## 0. How to use
File Structure
Sheet | Description
1. Effort | The sheet provides the overall effort to develop a end-to-end solution (based on the client need)
2. WBS | The sheet provides the work break down structure with the whole effort to complete the project.
2. Delivery Plan | The sheet provide the delivery plan, the resource allocation, the milestone
4. Master Data | The sheet provide the configuration to adjust the effort rate
Highlight | Remark
1 | Based on the client expectation & deliverables, BU can update the Module accordingly. Eg. If the client requests UI/UX design, please update the effort. Or, remove that row.
2 | in the "Fix SIT/UAT Issues" item, please provide your expected room for our client to handle the enhancement & the Change Request WITHOUT CHARGED.
3

## 1. Effort
24500
Effort By Module and Role
|  | Effort (MD) | [5 empty] | Cost (USD)
# | Module | Total (MD) | BE Coding (MD) | FE/Mobile Coding (MD) | Requirement Analysis (MD) | Testing (MD) | Project Management (MD) | Total (USD) | BE Coding (USD) | FE/Mobile Coding (USD) | Requirement Analysis (USD) | Testing (USD) | Project Management (USD)
I
I.A
II
II.A
II.B
III
III.A
III.B
TOTAL
TOTAL

## 2. WBS
|  | Project Code | BNK-LIB-001
WBS OF LIBRARY MVP
| # | Ref. Code | Features | Description | Total (MD) | BE Coding (MD) | FE/Mobile Coding (MD) | Requirement Analysis (MD) | Testing (MD) | Project Management (MD) | Remark
| I |  | Setup Phase |  |  |  | 2
A | I.A |  | Project Initialization |  |  |  | 2
| 1 |  | Project Kickoff and Setup | Setup project infrastructure, repository, and initial environment. |  |  | 2
| II |  | Development Phase |  |  | 13 | 9
A | II.A |  | Backend Development |  |  | 13
1 | II.A.1 |  | Book Management Module (Backend) |  |  | 9
| 2 |  | Develop Book CRUD APIs | Implement backend APIs for create, read, update, delete operations of book records. |  | 6
| 3 |  | Develop Search API for Books | Implement backend API for book search by title, author, or ISBN. |  | 3
2 | II.A.2 |  | User Management Module (Backend) |  |  | 4
| 4 |  | Develop User Authentication APIs | Implement backend authentication and authorization for library users. |  | 4
B | II.B |  | Frontend Development |  |  |  | 9
1 | II.B.1 |  | Book Management Module (Frontend) |  |  |  | 5
| 5 |  | Implement Book Management UI | Develop frontend interfaces for managing book records. |  |  | 5
2 | II.B.2 |  | User Management Module (Frontend) |  |  |  | 4
| 6 |  | Implement User Login UI | Develop frontend user login and registration pages. |  |  | 4
| III |  | Testing & Deployment Phase |  |  | 2 | 4
A | III.A |  | Testing |  |  | 1 | 3
| 7 |  | Functional Test of CRUD and Search APIs | Test backend APIs for book management and search feature. |  | 1 | 1
| 8 |  | UI Testing for Book and User Management | Test frontend UI components for book management and user login. |  |  | 2
B | III.B |  | Deployment & Release |  |  | 1 | 1
| 9 |  | Deployment to Test Environment | Deploy the application to a test environment for staging purposes. |  | 0.5 | 0.5
| 10 |  | Final Release and Documentation | Deploy to production environment and finalize project documentation. |  | 0.5 | 0.5

## 3. Delivery Plan (By Month)
Master Plan
| Master Planning |  |  | 1st Month |  | 2nd Month |  | 3rd Month |  | 4th Month |  | 5th Month |  | 6th Month |  | 7th Month |  | 8th Month |  | 9th Month
# | Module | Start | End | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18
| REQUIREMENT GATHERING | TBD | TBD
I |  | 2026-04-29 | 2026-04-29
I.A |  | 2026-04-29 | 2026-04-29
II |  | 2026-04-30 | 2026-05-08
II.A |  | 2026-04-30 | 2026-05-05
II.B |  | 2026-05-06 | 2026-05-08
III |  | 2026-05-11 | 2026-05-12
III.A |  | 2026-05-11 | 2026-05-11
III.B |  | 2026-05-12 | 2026-05-12
UAT
Nursing
# | Resource Planning | Start | End | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18
1 | Project Manager | TBD | TBD | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2
2 | Technical Lead |  |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
3 | Developer |  |  |  | 2 | 2 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 1 | 1 | 1 | 1
4 | Business Analyst | TBD | TBD | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
5 | Quality Controller | TBD | TBD |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
6 | Designer | TBD | TBD |  | 1 | 1
7 | Devops | TBD | TBD |  | 1 | [10 empty] | 0.2 |  | 0.2 |  |  |  | 682
TOTAL
# | Deliverables Milestone | Start | End | Deliverables
1 | Contract signoff | TBD | TBD | Contract Signoff
2 | Requirement Confirmation/Signoff | TBD | TBD | BRD
3 | Development Completion and UAT Initiation | TBD | TBD | System is ready in UAT + Test cases / Test Report
4 | Completion of UAT | TBD | TBD | Soure code + User Guide + Tech Specification
5 | Completion of Post-Launch Support | TBD | TBD

## 3. Delivery Plan
Master Plan
|  |  |  | 1st Month |  |  |  | 2nd Month |  |  |  | 3rd Month |  |  |  | 4th Month |  |  |  | 5th Month
| Master Planning |  |  | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4 |  | Sprint 5 |  | Sprint 6 |  | Sprint 7 |  | Sprint 8 |  | Sprint 9 |  | Sprint 10
# | Module | Start | End | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20
| REQUIREMENT GATHERING | TBD | TBD
I |  | 2026-04-29 | 2026-04-29
I.A |  | 2026-04-29 | 2026-04-29
II |  | 2026-04-30 | 2026-05-08
II.A |  | 2026-04-30 | 2026-05-05
II.B |  | 2026-05-06 | 2026-05-08
III |  | 2026-05-11 | 2026-05-12
III.A |  | 2026-05-11 | 2026-05-11
III.B |  | 2026-05-12 | 2026-05-12
UAT
Nursing
# | Resource Planning | Start | End | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W17 | W18
1 | Project Manager | TBD | TBD | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2 | Technical Lead
3 | Developer
4 | Business Analyst | TBD | TBD | 1 | 0.5
5 | Quality Controller | TBD | TBD |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
6 | Designer | TBD | TBD |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
7 | Devops | TBD | TBD |  | 0.2 | [8 empty] | 0.2 |  | 0.2
TOTAL
# | Deliverables Milestone | Start | End | Deliverables | [16 empty] | OB works with client to finalize this milestone
1 | Contract signoff | TBD | TBD | Contract Signoff
2 | Requirement Confirmation/Signoff | TBD | TBD | BRD
3 | Development Completion and UAT Initiation | TBD | TBD | System is ready in UAT + Test cases / Test Report
4 | Completion of UAT | TBD | TBD | Soure code + User Guide + Tech Specification
5 | Completion of Post-Launch Support | TBD | TBD

## 4. Master Data
BU
Role | Percent on Dev | Remark
PM | 0.05 | in total (dev + ba + qc)
BA | 0.1
Developer
QC | 0.3
OB
Role | Rate
PM | 500
BA | 400
Developer | 450
QC | 350

## 1. Effort Summary_By PP_BK (hidden)
2500000
Effort By Module and Role
# | Module |  | Total (MD) | BE (MD) | FE (MD) | BA (MD) | QC (MD) | PM (MD)
Client Portal
1
2
3
4
5
Admin Portal
1
2
3
4
Other
1 | - Multi Language - Integrate - Access Control - Integration with 3rd parties (KYC, Twilio)
Deployment
1 | Deployment + Solution Architecture (database design, setup source code BE/FE) |  | 10
TOTAL
Rate Card
# | Function | Daily Rate (€)
1 | S-PM
2 | S-BA
3 | M-DEV
4 | M-QA
5 | S-Devops
TOTAL
Costing
# | Module |  | Total (€) | BE (€) | FE (€) | BA (€) | QC (€) | PM (€) | Devops (€)
Client Portal
1 | Registration
2 | Login
3 | Dashboard
4 | Funder
5 | Account
Admin Portal
1 | Login
2 | Member
3 | KYC
4 | Admin
Other
1 | - Multi Language - Integrate - Access Control
Deployment
1 | Setup pipeline, CICD, deploy to DEV/UAT/PROD environment
TOTAL
Assuming the team will have 1 Technical Leader, 1 middle QC, 3 middle Dev, 1 Devops

## 3. WBS_General_BK (hidden)
WBS OF LENDING SYSTEM FOR PROPCAP
# | Ref. Code | Screen Name | Features | Total (MD) | BE | FE | BA | QC | PM (coordinate only) | Remark
Client Portal
Registration
1 | LS.CP-1 | Frontend-Registration | 1. Select Button 2. Corporate/Individual 3. Popup Warning (Popup-warning-cor) |  | 0.5 | 0
2 | LS.CP-2 | Frontend-Registration-form-cor | For Corporation 1. Validation handle 2. Create My Account/Receive direct marketing Check box 3. Platform Usage Disclaimer (Popup - Platform Usage Disclaimer – cor) 4. Term and Conditional (Popup - Terms and Conditions – cor) 5. Personal Data Privacy Policy (Popup - Personal Data Privacy Policy – cor) |  | 1 | 2
3 | LS.CP-3 | Frontend - ActiveAC – cor | For Corporation 1. Authentication 2. Resend/Submit |  | 0.5 | 0.5
4 | LS.CP-4 | Frontend - Registration – form | For Individual 1. Validation handle 2. Create My Account/Receive direct marketing Check box 3. Platform Usage Disclaimer (Popup - Platform Usage Disclaimer) 4. Term and Conditional (Popup - Terms and Conditions) 5. Personal Data Privacy Policy (Popup - Personal Data Privacy Policy) |  | 1 | 2
5 | LS.CP-5 | Frontend - ActiveAC | For Individual 1. Authentication 2. Resend/Submit |  | 0.5 | 0.5
Login
6 | LS.CP-4 | Frontend-Login | 1. Authentication 2. Forgot Password/Login Button |  | 0.5 | 1
7 | LS.CP-5 | Frontend-Login-OTP | 1. Auto send email OTP 2. Authentication OTP 3. Submit/Resend OTP |  | 0 | 0.5
8 | LS.CP-6 | Frontend - Forget Password | 1. Authentication 2. Request password reset/Back to Login 3. Send auto email |  | 0.5 | 0.5
Dashboard
9 | LS.CP-7 | Frontend - Dashboard - individual | 1. Navigation Menu 2. Become a Funder 3. Become a Borrower/Guarantor 4. Logout |  | 0.5 | 0.5
10 | LS.CP-8 | Frontend - Dashboard – DocsSubmitted | 1. Navigation Menu 2. Become a Funder/Become a Borrower 3. Status Management 4. Invest a deal/Submit a mortgage deal 5. Logout |  | 0.5 | 0.5
11 | LS.CP-9 | Frontend - FunderBorrower_Dashboard | 1. Navigation Menu 2. Invest a deal/Submit a mortgage deal 3. Logout |  | 0.5 | 0.5 |  |  |  | BnK Q&A (No.1) Maybe Design was wrong, this screen show when click proffile account
Funder
12 | LS.CP-10 | Frontend - Funder - Individual - Borrowers and Guarantors | Account Details 1. Process 5 Step 2. Select Currency/Personal Detail/Contact Detail 3. Save and Next/Cancel/Submit |  | 5 | 5
11 | LS.CP-11 | Frontend - Funder - Individual - Employment Details | Employment Details 1. Process 5 Step 2. Employment Details 3. Save and Next/Cancel/Submit/Back 4. Change status Previous Step and hint this step |  | 1 | 1
12 | LS.CP-12 | Frontend - Funder - Individual - Loan Lending Criteria | Loan Lending Criteria 1. Process 5 Step 2. Loan Lending Criteria 3. Save and Next/Cancel/Submit 4. Change status Previous Step and hint this step |  | 2 | 2
13 | LS.CP-13 | Frontend - Funder - Individual - Bank Ac | Bank Account Information 1. Process 5 Step 2. Bank Account Information 3. Save and Next/Cancel/Submit 4. Change status Previous Step and hint this step |  | 1 | 1
14 | LS.CP-14 | Frontend - Funder - Individual - SupportingDoc | Supporting Document 1. Process 5 Step 2. Personal Level 3. Save as Draft/Cancel/Submit/Dowload file/Delete File/ Upload file 4. Change status Previous Step and hint this step |  | 2 | 3
15 | LS.CP-15 | Frontend - Popup - Declaration Form | 1. Validation handle 2. Agree Button |  | 0.5 | 0.5
16 | LS.CP-16 | Frontend - Popup - Personal Information Collection Statement | 1. Validation handle 2. Agree Button |  | 0.5 | 0.5
17 | LS.CP-17 | Popup - PI - Funder - individual | 1. Validation handle 2. Agree Button |  | 0.5 | 0.5
Account
18 | LS.CP-18 | Frontend - Borrower_Account | Account Information Tab 1. Account Information/ Personal Details/Contact Detail/Notication/Change Password |  | 3 | 2
19 | LS.CP-19 | Frontend - Borrower_Account – Document List | Document List Tab 1. Borrower Request (Dowload file) 2. Funder Request |  | 0.5 | 0.5
Admin Portal
Login
20 | LS.AP-1 | Backend - Login | 1. Authentication 2. Forgot Password/Login Button |  | 1 | 1
21 | LS.AP-2 | Backend - forget password | 1. Authentication 2. Request password reset/Back to Login 3. Send auto email |  | 0.5 | 1
Member
22 | LS.AP-3 | Backend - Members - List of user | 1. Listing/Search/Sort/View/Reset/Paging/Add user/Dowload |  | 3 | 3
23 | LS.AP-4 | Backend - Members - Add User | 1. Auto-generate Password/Cancel/Submit |  | 1 | 1
24 | LS.AP-5 | Backend - Members - User detail - Basic Info. | Basic Information Tab 1. Edit/change status |  | 1 | 1
25 | LS.AP-6 | Backend - Members - User detail - Change Request | Change Request Tab 1. Listing/Sort/Add Change Request/Dowload/Save/Cancel/Delete 2. Status Management |  | 5 | 6
26 | LS.AP-7 | Backend - Members - User detail – Request of Funder -Individual | Funder Request Tab 1. Edit/Approve/Reject/KYC 2. Supporting Document Uploaded (List/Upload/Dowload/Delete) |  | 5 | 5
27 | LS.AP-8 | Backend - Members - User detail – Request of Borrower -Individual | Borrower/Guarantor Request Tab 1. Edit/Approve/Reject/KYC 2. Supporting Document Uploaded (List/Upload/Dowload/Delete) 3. Company KYC |  | 5 | 5
28 | LS.AP-9 | Backend - Members - User detail - Funder KYC_individual | Funder KYC Tab 1. Navigation mini (status management) 2. Edit/RunAML Screening Now/KYC Report/ Accept/Deny/Dowload/Go to Search/Full Detail/Add Comment 3. AML Checking 4. KYC Audit Trail (Paging) |  | 5 | 5
29 | LS.AP-10 | Backend - Members - User detail - Borrower KYC_corparate | Borrower/Guarantor KYC Tab 1. Navigation mini (status management) 2. Edit/RunAML Screening Now/KYC Report/ Accept/Deny/Dowload/Go to Search 3. Additional KYC Step (Add New Step/upload/Delete/Edit) 3. AML Checking 4. KYC Audit Trail (Paging) 5. Nova Credit (Generate Nova Credit Report) |  | 5 | 5
30 | LS.AP-11 | Backend - Members - User detail - Activity Log | Activity Log Tab 1. Listing/Sort/Dowload/Paging 2. Get all data activity |  | 0.5 | 1
31 | LS.AP-12 | Backend - Members - List of Request | 1. Listing/Sort/Search/Reset/Dowload/Paging 2. Status Management |  | 1 | 1.5
32 | LS.AP-13 | Backend - Members - List of Change Request | 1. Listing/Sort/Search/Reset/Dowload/Paging 2. Status Management |  | 1 | 1.5
33 | LS.AP-14 | Backend - Members - Add Change Request | 1. Search 2. Search Result (Backend - Members - Add Change Request – 1) |  | 3 | 3
KYC
33 | LS.AP-14 | Backend - KYC - List of kyc | 1. Listing/Sort/Search/Reset/Dowload/Paging 2. Status Management |  | 1 | 1.5
34 | LS.AP-15 | Backend - KYC - Alert List | 1. Listing/Sort/Search/Reset/Dowload/Paging 2. Status Management 3. Alert |  | 1 | 2
35 | LS.AP-16 | Backend - KYC - Repositry | 1. Listing/Sort/Search/Reset/Dowload/Paging 2. Status Management |  | 1 | 1.5
Admin
36 | LS.AP-17 | Backend - Admin - Audit Log List | 1. Listing/Sort/Search/Reset/Dowload/Paging 2. Get all data audit log |  | 0.5 | 1
37 | LS.AP-18 | Backend - Admin - Holiday Table | 1. Listing/Sort/Search/Import/Export 2. Validate upload data |  | 1 | 1
38 | LS.AP-19 | Backend - Admin - Currency Exchange | 1. Listing/Sort/Import/Export 2. Validate upload data |  | 1 | 1
Other
39 | LS.AP-20 | Multi Language | 1. Change Language (English , Traditional Chinese and Simplified Chinese) |  | 2 | 0
40 | LS.AP-21 | Integrate | Twilio (OTP): call API for generating OTP + verify OTP |  | 0 | 5 |  |  |  | Spent time for research
41 | LS.AP-22 |  | Email: sending email + content for each use case |  | 0 | 5 |  |  |  | Spent time for research
42 | LS.AP-23 |  | Integrate with 3rd party API for KYC |  | 0 | 5 |  |  |  | Spent time for research
43 | LS.AP-24 | Access Control | For both Client Site and Admin Site (Only Screen + Key button (Accept/Deny)) 1. Client Site (Borrower/Funder/Nomineee) 2. Admin Site (Operation Team - General User/Operation Team - Operation Head (Approver)/IT Administrator (Super User) |  | 2 | 3

## 1. Effort Summary_General (hidden)
2500000
TGP for TG SPROUT
# | Task | Estimate (MD) | Unit Price | TOTAL | REMARK
1 | UIUX Design | 0 | 0 |  | user customer design
2 | Collect Requirement + Wrire SRS |  | 0 |  | 1. Collect + clarify + wireframe for new changes 2 Making documents : SRS, user guide 3. BA effort to follow up with developers to transfer requirements and validate output within the project timeline
3 | Solution + Coding |  | 0 |  | Do technical solution and coding to implement features/fix bugs
4 | Test plan/test cases + execute test |  | 0 |  | Output: test cases + execute test. QC tasks (cycle for each sprint): 1. Study requirements from BA/PM/Customers 2. Create test cases, making Testcase documents 3. Execute test 4. Log bugs + followup with dev to re-test + report to PM for testing progress/outstanding issues. 5. Regresstion test all feature before handover to UAT + before releasing to PROD.
5 | Setup + Deploy DEV/UAT + writing guideline | 8 | 0 |  | Do below tasks for each environment (DEV/UAT). If customer need us help to deploy on PROD, we can help also. 1. Create deployment pipeline in gitlab: build job + deploy job for each Microservice. (< 10 Microservice) 2. Verify to make sure these MS can call togethers. 3. Show logs for each MS. (It's for developers to troubelshoot when having issues in these invironments)
6 | Support users during UAT | 30 | 0 |  | UAT within 3 weeks. 1 dev and 1 BA/QC will support to test/fix bugs within this period
7 | Project Management and Teamwork |  | 0 |  | PM Effort (planning, executing, monitoring & controlling, directing, closing) + All team member effort for communication/grooming/planning/demo/retrospective to ensure for progress and quality
TOTAL
Post Golive support
# | Task | Support Duration (month) | Delivery Service (VND) | TOTAL (VND) | REMARK
1 | Support 3 months. | 3 |  |  | 1% total delivery service for each month
TOTAL
(VND)
(USD)